NON-CONFORMANCE REPORT (NCR)

NCR Number: NCR-2024-003

Date Raised: 15 February 2024

Project: PMO-2024-CV-001 - Pilbara Iron Ore Conveyor Components

Raised By: Jennifer Walsh, QC Inspector

Department: Quality Control

DESCRIPTION OF NON-CONFORMANCE:

During routine dimensional inspection of conveyor support structure CS-008, the following discrepancies were identified:

1. Overall height dimension: 1,847mm (Drawing specification: 1,850mm ± 3mm)

2. Bolt hole centres: 398mm (Drawing specification: 400mm ± 1mm)

3. Weld profile on connection plate exceeds maximum throat thickness by 2mm

DETECTION METHOD:

Routine dimensional inspection using calibrated measuring equipment

- Steel rule (Cal. Cert: SR-2023-089, Due: 15/03/2024)

- Vernier callipers (Cal. Cert: VC-2023-156, Due: 22/02/2024)

- Weld gauge (Cal. Cert: WG-2023-078, Due: 10/04/2024)

ROOT CAUSE ANALYSIS:

Primary Cause: Incorrect setup of welding jig during assembly

Contributing Factors:

- Jig calibration overdue by 2 weeks

- Operator training on new jig setup incomplete

- Work instruction WI-2024-CS-008 Rev B not followed correctly

IMMEDIATE ACTION TAKEN:

1. Item CS-008 quarantined in designated area

2. Production stopped on similar items (CS-009 to CS-012)

3. Supervisor notified: Mark Stevens

4. Customer notification: Not yet completed

PROPOSED CORRECTIVE ACTION:

1. Re-calibrate welding jig per procedure CAL-JIG-001

2. Rework CS-008 to correct dimensional issues

3. Re-train assembly operators on jig setup procedures

4. Update work instruction to include additional checkpoints

PROPOSED PREVENTIVE ACTION:

1. Implement daily jig verification checks

2. Review calibration schedule for all assembly fixtures

3. Enhance operator training program

4. Install visual aids at workstation

IMPACT ASSESSMENT:

Schedule Impact: 2 days delay on delivery milestone

Cost Impact: $3,200 (rework labour + materials)

Customer Impact: Potential delivery delay

Quality Impact: No safety implications identified

DISPOSITION:

☐ Use as is

☐ Repair

☒ Rework

☐ Scrap

☐ Return to supplier

REWORK DETAILS:

1. Machine bolt holes to correct centres using drill press

2. Grind excess weld material to specification

3. Re-inspect all dimensions per drawing PMO-CV-001-CS-008 Rev C

4. Update inspection records

VERIFICATION OF CORRECTIVE ACTION:

Action Owner: Mark Stevens, Production Supervisor

Target Completion: 20 February 2024

Verification Method: Re-inspection by independent QC inspector

APPROVALS:

Quality Manager: David Thompson

Date: 15/02/2024

Signature: D. Thompson

Production Manager: Sarah Chen

Date: 16/02/2024

Signature: S. Chen

Customer Notification Required: YES ☒ NO ☐

Customer Notified By: ________________

Date: ________________

CLOSURE:

Corrective Actions Completed: ☐ YES ☐ NO

Verified By: ________________

Date: ________________

NCR Closed By: ________________

Date: ________________

Note: This NCR contains intentional procedural errors for training purposes.