## production_schedule
Week | Start Date | End Date | Activity | Resource | Planned Hours | Actual Hours | Status | Notes
1 | 2024-01-15 | 2024-01-19 | Material procurement | Purchasing | 40 | 42 | Complete | Delivery delayed by 1 day
2 | 2024-01-22 | 2024-01-26 | Cutting operations | CNC Operator A | 80 | 85 | Complete | Additional setup time required
2 | 2024-01-22 | 2024-01-26 | Cutting operations | CNC Operator B | 80 | 78 | Complete
3 | 2024-01-29 | 2024-02-02 | Welding - Batch 1 | Welder Team 1 | 120 | 135 | Complete | Rework required on 3 units
3 | 2024-01-29 | 2024-02-02 | Welding - Batch 1 | Welder Team 2 | 120 | 118 | Complete
4 | 2024-02-05 | 2024-02-09 | Welding - Batch 2 | Welder Team 1 | 120 | 125 | Complete
4 | 2024-02-05 | 2024-02-09 | Quality inspection | QC Inspector | 40 | 45 | Complete | Additional testing required
5 | 2024-02-12 | 2024-02-16 | Assembly operations | Assembly Team | 160 | 170 | Complete | Overtime required
6 | 2024-02-19 | 2024-02-23 | Surface preparation | Prep Team | 80 | 88 | Complete | Weather delays affected outdoor work
7 | 2024-02-26 | 2024-03-01 | Galvanising | External Supplier | 0 | 0 | Complete | Subcontracted work
8 | 2024-03-04 | 2024-03-08 | Final inspection | QC Inspector | 32 | 35 | Complete
8 | 2024-03-04 | 2024-03-08 | Packaging | Logistics Team | 24 | 22 | Complete
9 | 2024-03-11 | 2024-03-15 | Delivery - Stage 1 | Transport | 16 | 18 | Complete | Traffic delays
10 | 2024-03-18 | 2024-03-22 | Welding - Batch 3 | Welder Team 1 | 120 | 140 | In Progress | Behind schedule due to material shortage
10 | 2024-03-18 | 2024-03-22 | Welding - Batch 3 | Welder Team 2 | 120 | 95 | In Progress | Team member on sick leave
11 | 2024-03-25 | 2024-03-29 | Assembly - Batch 2 | Assembly Team | 160 | 0 | Planned
12 | 2024-04-01 | 2024-04-05 | Final QC - Batch 2 | QC Inspector | 40 | 0 | Planned